Strategic Plan for E-Governance Data Collection

A Blueprint for Gathering, Validating, and Utilizing Publicly Available Governance Data

Week 1 Deliverable  |  Prepared: August 30, 2026

# 1. Objective

This strategic plan defines a structured, repeatable methodology for collecting, validating, and organizing publicly available data relevant to e-governance performance. The purpose is to build a defensible evidence base — drawn entirely from open, legitimately accessible sources — that can be used to track how governments deploy digital tools to deliver public services, engage citizens, and build institutional capacity.

The plan is scoped as a Week 1 foundation: it establishes objectives, sources, methodology, a timeline, and a risk framework so that subsequent weeks can move directly into data acquisition and analysis without re-litigating scope or method.

## 1.1 Specific Goals

- Identify a core set of internationally recognized e-governance indicators (service delivery, infrastructure, human capital, participation, and open data maturity).

- Map each indicator to at least one authoritative, publicly available dataset or portal.

- Design a collection methodology that is legal, reproducible, and low-risk to the source systems being accessed.

- Define quality thresholds so that only accurate, timely, and comparable data enters the working dataset.

- Produce a timeline and risk register that a small team can execute against without further scoping work.

# 2. Background: The Role of Data in E-Governance

E-governance performance is increasingly measured through composite, internationally benchmarked indices rather than isolated statistics. The United Nations E-Government Survey, published by UN DESA, is the primary global benchmark and scores all 193 Member States on the E-Government Development Index (EGDI), a composite of three equally weighted sub-indices.

- Online Services Index (OSI) — breadth, depth, and usability of government digital services.

- Telecommunication Infrastructure Index (TII) — connectivity and access (internet users, mobile/fixed broadband, subscriptions).

- Human Capital Index (HCI) — literacy, enrolment, and education levels underpinning digital readiness.

The Survey also tracks a distinct E-Participation Index (EPI) and, at the city level, a Local Online Service Index (LOSI). Alongside these, growth in Open Government Data (OGD) has been substantial: the number of countries operating national OGD portals rose from 46 in 2014 to 153 in 2020, with associated practices such as published OGD policies, metadata standards, and public data-request channels becoming increasingly common. This shift means credible e-governance research must combine composite index data with granular, country-level open datasets to explain the mechanisms behind index scores.

# 3. Scope and Planning

## 3.1 Type of Data Required

| Category | Examples | Typical Format |
| --- | --- | --- |
| Composite indices | EGDI, OSI, TII, HCI, EPI, LOSI | CSV / XLSX / PDF tables |
| Infrastructure & access | Internet penetration, broadband subscriptions, mobile coverage | API / CSV (ITU, World Bank) |
| Service delivery | Number of digital services, transactional service availability | Portal listings, national OGD portals |
| Participation | E-consultation, e-decision-making features, social media use by government | Survey annexes, portal crawls |
| Open data maturity | OGD policy existence, metadata standards, portal feature counts | OGD Index, ODIN, Global Open Data Index |
| Governance context | Rule of law, corruption perception, regulatory quality | World Bank WGI, Transparency International |

## 3.2 Collection Frequency

- Composite indices (EGDI, EPI, LOSI): biennial pull, aligned to UN Survey release cycle.

- Infrastructure statistics (ITU, World Bank): annual pull, with a mid-year check for revisions.

- Open data portal metadata: quarterly crawl to detect newly published or removed datasets/features.

- Governance context indicators (WGI, CPI): annual pull, aligned to publisher release schedule.

# 4. Methodology

Collection will use a tiered approach, preferring the most structured and least intrusive method available for each source, in this priority order:

- Official APIs / bulk downloads — e.g., World Bank API, ITU DataHub bulk files, UN Data API. Preferred wherever available; produces structured, versioned data with minimal load on source servers.

- Structured file downloads — CSV/XLSX annexes published alongside reports (e.g., UN E-Government Survey technical appendix), parsed with schema-validated scripts rather than manual re-typing.

- Controlled web scraping — used only for public portal metadata not exposed via API (e.g., counting features on national OGD portals), performed at low request rates, respecting robots.txt and terms of service, and logged for auditability.

- Manual collection — reserved for small, non-recurring items (e.g., verifying a specific portal feature) where automation is not cost-effective; always double-entered by a second reviewer.

Below is the intended data flow from source identification through to a usable, quality-scored dataset:

Figure 1: End-to-end data collection pipeline, from source scoping through to the indicator dashboard.

# 5. Data Sources

| Source | Custodian | Access Method |
| --- | --- | --- |
| UN E-Government Survey / EGDI, EPI, LOSI | UN DESA (Division for Public Institutions and Digital Government) | Bulk CSV/XLSX + UNeGovKB online database |
| World Development Indicators | World Bank | REST API + bulk CSV |
| ICT Statistics / connectivity data | International Telecommunication Union (ITU) | DataHub bulk download |
| Worldwide Governance Indicators (WGI) | World Bank | Bulk CSV / API |
| Corruption Perceptions Index | Transparency International | Annual CSV release |
| Open Data Inventory (ODIN) / Global Open Data Index | Open Data Watch / Open Knowledge Foundation | Published rankings + methodology CSVs |
| National Open Government Data portals | Individual national governments | Portal metadata (API where offered, else controlled crawl) |

All sources listed are publicly published for research and policy use. No source requiring authentication, paid licensing, or terms that prohibit redistribution will be used without separate legal review.

# 6. Validation and Quality Framework

## 6.1 Quality Dimensions

| Dimension | Definition | Metric / Threshold |
| --- | --- | --- |
| Relevancy | Indicator maps clearly to a defined e-governance construct | Mapped to indicator taxonomy; unmapped fields excluded |
| Timeliness | Data reflects the most recent available reporting cycle | Flagged if source data is older than 2 reporting cycles |
| Accuracy | Values match the original publisher figures | 100% match on spot-checked sample (≥10% of records) |
| Completeness | Required fields populated for the country/entity set in scope | ≥95% field completeness before inclusion |
| Comparability | Consistent units, definitions, and time periods across countries | Standardized via a shared schema and unit-conversion layer |

## 6.2 Validation Steps

- Automated schema validation on ingest (data types, ranges, required fields) with failed records quarantined, not silently dropped.

- Cross-source reconciliation — where two sources report the same underlying metric (e.g., internet penetration from both ITU and World Bank), values are compared and discrepancies above a defined tolerance are flagged for manual review.

- Provenance logging — every record retains its source URL, retrieval date, and collection method for full auditability.

- Second-reviewer sign-off on any manually collected or scraped field before it enters the working dataset.

- Periodic re-validation — a rolling 10% sample of the dataset is re-checked against source each quarter to catch silent source-side changes.

# 7. Timeline

| Phase | Duration | Key Activities |
| --- | --- | --- |
| Phase 1 — Scoping & Source Mapping | Week 1 | Finalize indicator list, confirm source access terms, draft this strategic plan |
| Phase 2 — Tooling & Pipeline Setup | Weeks 2–3 | Build API connectors, scraping scripts (where needed), and the schema-validation layer |
| Phase 3 — Initial Collection | Weeks 4–5 | Pull composite indices and infrastructure data; populate baseline dataset |
| Phase 4 — Validation & Cleaning | Week 6 | Run cross-source reconciliation, completeness checks, manual spot-checks |
| Phase 5 — Dashboard & Reporting | Weeks 7–8 | Build indicator dashboard, document methodology, deliver first analytical output |
| Phase 6 — Ongoing Maintenance | Continuous | Quarterly/annual refresh cycles per source cadence; rolling re-validation sample |

# 8. Expected Challenges and Mitigation Strategies

| Challenge | Risk Level | Mitigation Strategy |
| --- | --- | --- |
| Inconsistent definitions/units across sources (e.g., differing 'internet user' definitions) | High | Adopt a documented mapping schema; store both raw and normalized values |
| Source portals change structure or block automated access | Medium | Prefer official APIs/bulk files first; rate-limit and monitor scrapers; maintain fallback manual procedure |
| Infrequent update cycles (e.g., EGDI is biennial) creating stale indicators between releases | Medium | Blend index data with more frequent proxy indicators (e.g., annual ITU connectivity data) and clearly label data vintage |
| Missing or incomplete data for smaller/lower-income countries | Medium | Flag gaps explicitly rather than imputing; report coverage rate alongside findings |
| Legal/terms-of-service constraints on redistribution | Medium | Legal review of each source's terms before ingestion; store links/citations rather than redistributing restricted content where required |
| Human error in manual collection steps | Low–Medium | Mandatory second-reviewer double-entry and periodic re-validation sampling |
| Team capacity constraints in later automation phases | Low | Prioritize high-value indicators first; phase automation incrementally per the timeline |

# 9. Conclusion

This plan establishes a clear, phased, and auditable approach to collecting e-governance data from legitimate public sources. By anchoring the indicator set to established international frameworks (EGDI, EPI, LOSI, WGI, and open-data maturity indices) and pairing collection methods with an explicit quality and validation framework, the resulting dataset will be defensible, comparable across countries, and ready to support analysis and reporting in subsequent project phases.